## Table 1
PROJECT COST BID SHEET |  |  |  | DATE:
PROJ: | Yates Complex Electrical Rehab | Estimator:
LOC: | Lead, SD | Contractor:
Item | DESCRIPTION | Line Total
Item A: Administration Building: Procurement, Installation, and Demolition
| oAdmin Bldg - Transformer (480V-208Y/120V 225KVA) oAdmin Bldg to Crusher Bldg Buried Conduit oAdmin Bldg to Crusher Bldg Cable oAdmin Bldg to Crusher Bldg Galvanized Conduits and Supports oDemo Admin Transformer (2400 V to 208 V) oDemo Admin 2.4 kV Fused Disconnect | 0
Line Total
Item B: E&O Building: Procurement, Installation, and Demolition
| oE&O - Transformer (225KVA) oE&O - Transformer Pad oE&O - Reroute 480V Cable (Crusher Substation to Transformer) oE&O - Panelboard oE&O - Transformer to Panelboard Conduit oE&O - Transformer to Panelboard Cable oDemo E&O Building Transformer (2400 V to 120/240 V) oDemo E&O Building Transformer (2400 V to 480 V) oDemo E&O Building Transformer (2400 V to 208 V) | 0
Line Total
Item C: Yates Crusher/Headframe Building: Procurement and Installation
| oCrusher Bldg - Repurpose 480V Power Panel oCrusher - Switchboard oCrusher Bdlg - 1200A, Switchgear oCrusher Bldg - Switchgear Pad oCrusher Bldg - 2000KVA Transformer oCrusher Bldg - Transformer Pad oCrusher Bldg - Transformer Berm oCrusher Bldg - Feed to wall for Admin bldg oCrusher Bldg - Feed for 480V POWER PANEL oCrusher Bldg - Feed to HeadFrame Bldg (100 kVA) oCrusher Bldg - Feed to Switchboard oCrusher Bdg - Cable Tray oCrusher Bldg - 3 - 4" RGS conduit - 2 for Repurpose panel & 1 for Admin bldg oCrusher Bldg - Feed to 2000kVA Transformer oCrusher Bldg - H-Frame to Support Cable Tray from shaft to Crusher Building oCrusher Bldg - Manhole (MH1) oCrusher Bldg - Manhole (MH1) Termination Box oCrusher Bldg to MH1 Duct Bank w/ Conduit oCrusher Bldg to MH1 Cable (Main Feed) oCrusher Bldg to MH1 Cable (East Switchyard Feed) | 0
Line Total
Item D: Yates Hoist Building: Procurement, Installation, and Demolition
| oCrusher Bldg - Feed to Yates Hoist Building (Cable to Hoist MG Set Basement) | 0
Line Total
Item E: Commissioning and Miscellaneous
| oContractor - Testing and Commissioning oMisc Electrical Consumables oElectrical Grounding oContractor - Mob/Demob oContractor - Project Management, Site Supervision, Distributables, Operating Supplies, etc. oContractor - Engineering Suppport (Shop Drawings, Vendor Drawings, Construction Support, etc.) | 0
Line Total
Item F: General Construction
| oContractor Fees, Overhead, and Profit oSales and Excise Taxes oPayment and Performance Bonds oBuilder's Risk Insurance oContingency | 0
| TOTAL (Item A + B + C + D + E+F): These activites are also referenced in Section 4 of the RFP | 0
Engineering and Submittals |  |  |  | Calendar Days
Procurement and Lead Time |  |  |  | Calendar Days
Contractor Mobilization |  |  |  | Calendar Days
Construction: Installation, Commissioning, and Demolition |  |  |  | Calendar Days
Contractor Demobilization |  |  |  | Calendar Days
PROJECT COMPLETE (total days) |  |  | 0 | Calendar Days After Kickoff/NTP