## Sheet1
CARR COATINGS LLC: QUALITY ASSURANCE PLAN FOR YATES SURPLUS CONVEYANCE SANDBLAST & PAINTING
Transportation - North Work Deck & South Skip Bonnet
DEFINABLE FEATURE OF WORK: Loading & Transport to Off-Site Shop
CQC # | CQC FUNCTION TO BE VERIFIED | Contract (RFP) Ref. | Requirement | Measured "Actual" Value | Date Verified | Initials | Date Results/Notes Submitted to SDSTA
1.0.1 | Preliminary Meeting
1.0.2 | Palletize small parts, and secure/tag/label smaller components |  | Lifting Comp & Handrails
1.0.3 | Prepare all pieces for Transport - transportation arrangements & schedule
1.0.4 | Secure load(s) and Transport to off-site shop
Sandblasting & Cleaning - North Work Deck & South Skip Bonnet
DEFINABLE FEATURE OF WORK: Sandblasting North Work Deck & South Skip Bonnet
CQC # | CQC FUNCTION TO BE VERIFIED | Contract (RFP) Ref. |  |  | Date Verified | Initials | Date Results/Notes Submitted to SDSTA
2.0.1 | Preliminary Meeting
2.0.2 | North Work Deck sandblast aluminim handrail & aluminum decking components |  | SSPC-SP10 / NACE 2
2.0.3 | North Work Deck sandblast structural steel & steel tie-off point components |  | SSPC-SP10 / NACE 2
2.0.4 | Owner HOLD point - Owner perform thickness measurements on tower structural steel for baseline
2.0.5 | North Work Deck final clean for primer application
2.0.6 | South Skip Bonnet sandblast structural steel |  | SSPC-SP10 / NACE 2
2.0.7 | Owner HOLD point - Owner perform thickness measurements on tower structural steel for baseline
2.0.8 | South Skip Bonnet final clean for primer application
Primer & Painting Applications - North Work Deck & South Skip Bonnet
DEFINABLE FEATURE OF WORK: Primer & Painting Application
CQC # | CQC FUNCTION TO BE VERIFIED | Contract (RFB) Ref. |  |  | Date Verified | Initials | Date Results/Notes Submitted to SDSTA
3.0.1 | Preliminary Meeting
3.0.2 | Material Supply and Specification Compliance - Materials match specified products
3.0.3 | Epoxy primer mixing ratio verified and follows manufacturer recommendations
3.0.4 | Environmental Temperature measurement - log temperature at each application |  | Above 0 deg C
3.0.5 | Product Temperature measurement - log temperature at each application |  | above 10 deg C
3.0.6 | 1st Coat thickness verification |  | 2.0-5.0 mils
3.0.7 | 2nd Coat thickness verification |  | 4.0-6.0 mils
3.0.8 | Top Coat thickness verification |  | 3.0-7.0 mils
3.0.9 | Time log maintained for each application placement & dry time obtained
3.0.10 | Final touch-up and preparation for transport
Transportation - North Work Deck & South Skip Bonnet
DEFINABLE FEATURE OF WORK: Loading & Transport back to Owner Site
CQC # | CQC FUNCTION TO BE VERIFIED | Contract (RFB) Ref. |  |  | Date Verified | Initials | Date Results/Notes Submitted to SDSTA
4.0.1 | Preliminary Meeting
4.0.2 | Palletize small parts, and secure/tag/label smaller components |  | Lifting Comp & Handrails
4.0.3 | Prepare all pieces for Transport - transportation arrangements & schedule
4.0.4 | Secure load(s) and Transport to Owner Site
4.0.5 | Touch-up and final acceptance